## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Research data points on reservation systems and enhancement |  | 2018-01-08 | 2018-01-15 | 7 | Carmen | 100% | bar: WEEK 1 W to WEEK 2 R
Gather historical data on booking process |  | 2018-01-15 | 2018-01-15 | 0 | Carmen | 100% | bar: WEEK 2 T
Align and evaluate stakeholders |  | 2018-01-15 | 2018-01-17 | 2 | Alex | 100% | bar: WEEK 2 T to WEEK 2 R
Calculate projections and enhancements |  | 2018-01-17 | 2018-01-18 | 1 | Carmen | 100% | bar: WEEK 2 R to WEEK 2 F
Interview members of the staff |  | 2018-01-18 | 2018-01-19 | 1 | Alex | 100% | bar: WEEK 3 M
Create project charter (scope and goals) |  | 2018-01-22 | 2018-01-26 | 4 | Carmen | 100% | bar: WEEK 3 T to WEEK 3 F
Schedule kick off meeting |  | 2018-01-29 | 2018-01-29 | 0 | Carmen | 100% | bar: WEEK 3 F
Research reservation system options |  | 2018-02-02 | 2018-02-02 | 0 | Carmen | 100% | bar: WEEK 4 W to WEEK 5 M
Generate quotes and review costs |  | 2018-02-05 | 2018-02-05 | 0 | Carmen | 100% | bar: WEEK 4 F to WEEK 5 T
Test out reservation systems |  | 2018-02-05 | 2018-02-09 | 4 | Makayla | 100% | bar: WEEK 4 F to WEEK 5 W
Choose a reservation system |  | 2018-02-05 | 2018-02-09 | 4 | Carmen | 100% | bar: WEEK 5 T to WEEK 5 F
Vendor timeline and deliverables schedule |  | 2018-02-06 | 2018-02-10 | 4 | Carmen | 100% | bar: WEEK 5 T to WEEK 5 F
Create contracts and statements of work for vendors |  | 2018-02-12 | 2018-02-15 | 3 | Vince | 100% | bar: WEEK 6 W to WEEK 6 F
Message about launch date to stakeholders |  | 2018-02-13 | 2018-02-13 | 0 | Alex | 100% | bar: WEEK 7 T
Project Plan Updates |  | 2018-02-15 | 2018-02-28 | 13 | Carmen | 100% | bar: WEEK 7 M to WEEK 9 F
Update marketing/social media plan/calendar |  | 2018-02-15 | 2018-02-25 | 10 | Alex | 100% | bar: WEEK 7 R to WEEK 9 W
Create launch day plan: staffing, troubleshooting, etc. |  | 2018-02-18 | 2018-02-25 | 7 | Alex | 100% | bar: WEEK 8 T to WEEK 9 W
Map out seating chart/upload into software |  | 2018-02-20 | 2018-02-22 | 2 | Makayla | 100% | bar: WEEK 10 T to WEEK 10 W
Train GMs on new software |  | 2018-02-23 | 2018-02-23 | 0 | Makayla | 100% | bar: WEEK 10 R
Train staff on new software |  | 2018-02-24 | 2018-02-24 | 0 | Makayla | 100% | bar: WEEK 10 F
Test run reservation system |  | 2018-02-25 | 2018-02-25 | 0 | Makayla | 100% | bar: WEEK 11 M
Create troubleshoot/support plan |  | 2018-02-20 | 2018-02-25 | 5 | Makayla | 100% | bar: WEEK 10 T to WEEK 11 M
Launch day |  | 2018-03-01 | 2018-03-01 | 0 | Carmen | 100% | bar: WEEK 11 M; WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Research data points on reservation systems and enhancement |  | 7 | 5 | 7 | 14 | L
Gather historical data on booking process |  | 0 | 0 | 0 | 3 | H
Align and evaluate stakeholders |  | 2 | 0 | 2 | 5 | M
Calculate projections and enhancements |  | 1 | 1 | 1 | 4 | H
Interview members of the staff |  | 1 | 1 | 1 | 4 | H
Create project charter (scope and goals) |  | 4 | 2 | 4 | 11 | L
Schedule kick off meeting |  | 0 | 0 | 0 | 3 | H
Research reservation system options |  | 0 | 0 | 0 | 3 | H
Generate quotes and review costs |  | 0 | 0 | 0 | 3 | H
Test out reservation systems |  | 4 | 2 | 4 | 11 | L
Choose a reservation system |  | 4 | 2 | 4 | 11 | L
Vendor timeline and deliverables schedule |  | 4 | 2 | 4 | 11 | L
Create contracts and statements of work for vendors |  | 3 | 1 | 3 | 10 | L
Message about launch date to stakeholders |  | 0 | 0 | 0 | 3 | H
Project Plan Updates | Still waiting on Carter for the finalized menu and coupon value mock-ups for upload (aiming for one week but could extend to two); | 13 | 11 | 13 | 20 | L
Update marketing/social media plan/calendar | Once mock-ups are received, 3-4 hours to upload | 10 | 8 | 10 | 17 | L
Create launch day plan: staffing, troubleshooting, etc. | Projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems, Possible need to upgrade the POS system if S&S is running an older version (3-4 days), Electrician is confident they can wire both locations in two business days (16 hours), but since we can’t close the restaurants for a full day we need to schedule two half-days at each location | 7 | 5 | 7 | 14 | L
Map out seating chart/upload into software | The preparations and planning for the trainings should take about one week. | 2 | 0 | 2 | 9 | L
Train GMs on new software | Seydou will train managers first (2 hours), then managers will train all the staff at each location (2 hours for each training plus one hour before and after each training for facilitator prep/debrief) | 0 | 0 | 0 | 3 | H
Train staff on new software | Pre-training meeting to introduce tablets and changes to staff before training them on the tablets (1 hour at each location); Gilly and Alex will coordinate with Peta to schedule staff trainings at each of their locations. Each part of the training (pre-training, manager training, staff training) will take place on different days. | 0 | 0 | 0 | 3 | H
Test run reservation system |  | 0 | 0 | 0 | 3 | H
Create troubleshoot/support plan |  | 5 | 3 | 5 | 12 | L
Launch day |  | 0 | 0 | 0 | 3 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant Innovation, Technology Trends & Statistics | https://www.escoffier.edu/blog/world-food-drink/restaurant-innovation-technology-trends-statistics/ | 2025-06-23 | Provides statistics on customer preferences for technology in restaurants, generational differences, investment trends, and the impact on tipping. Last updated October 29, 2024.
The Ultimate Guide to Choosing a Restaurant Tablet Ordering System | https://www.peblla.com/blog/the-ultimate-guide-to-choosing-a-restaurant-tablet-ordering-system | 2025-06-23 | A comprehensive guide covering user interface, menu customization, POS integration, reliability, security, table layout planning, staff training, and promotion. Last updated February 26, 2025.
Case Study: Scaffidi Restaurant Group | https://squareup.com/us/en/the-bottom-line/case-studies/case-study-scaffidi-restaurant-group | 2025-06-23 | Case study on Scaffidi's Restaurant & Tavern's implementation of a tableside POS system, detailing challenges and positive outcomes like increased sales and reduced errors. Last updated May 19, 2022.
The Impact of Restaurant Tablets on Table Turnover and Revenue | https://madmobile.com/blog/impact-of-restaurant-tablets-on-table-turnover-and-revenue/ | 2025-06-23 | Discusses how tablets boost revenue through increased sales, faster table turnover, and operational efficiency, referencing a Wharton School study. Last updated March 1, 2024.
Challenges of Implementing Restaurant Table Ordering | https://madmobile.com/blog/challenges-of-implementing-restaurant-table-ordering/ | 2025-06-23 | Covers challenges in technical integration, staff training, customer acceptance, financial considerations, and security, with proposed solutions. Last updated June 28, 2024.
Research: Technology-Driven Growth Fuels 8% Profit Gains for Quick Service Restaurants | https://restauranttechnologynews.com/2025/05/research-technology-driven-growth-fuels-8-profit-gains-for-quick-service-restaurants/ | 2025-06-23 | PAR Technology's 2025 QSR Operational Index Report, highlighting growth in digital channels and rising labor costs. Last updated May 7, 2025.
Developing a Restaurant Tablet Implementation Plan for Success | https://madmobile.com/blog/challenges-of-implementing-restaurant-table-ordering/ | 2025-06-23 | Outlines an implementation plan covering technical integration, staff training, customer education, financial considerations, and security. Last updated March 8, 2024.
Restaurant EPOS System Case Study – Hannah | https://gardiffepos.com/blog/restaurant-epos-system-case-study-hannah/ | 2025-06-23 | Case study of a restaurant implementing a Gardiff EPOS system with tablet ordering, detailing the solution, delivery, and benefits. Last updated August 22, 2024.
Restaurant Tablet Best Practices | https://www.cuboh.com/blog/restaurant-tablet-best-practices | 2025-06-23 | Provides best practices for using tablets in restaurants, including menu design, software updates, staff training, and security.
Restaurant Tablet Ordering & Tableside Systems | https://hashmato.com/restaurant-tablet-ordering-tableside-systems/ | 2025-06-23 | Explains the functionality and benefits of tablet ordering systems, including increased revenue, reduced labor costs, and data-driven decision-making.
Digital Menus for Restaurants: A Step-by-Step Guide | https://sundayapp.com/digital-menus-for-restaurants-a-step-by-step-guide/ | 2025-06-23 | A guide to implementing digital menus, from setting goals and choosing a platform to designing the menu, training staff, and gathering feedback.
12 Successful Upselling Techniques for Restaurants | https://blog.menuviel.com/12-successful-upselling-techniques-for-restaurants/ | 2025-06-23 | Details various upselling techniques, including using descriptive language, suggesting pairings, and leveraging digital tools like POS prompts and tablet menus.
Tabletop tablets speed up restaurant service | https://www.cbsnews.com/news/tabletop-tablets-speed-up-restaurant-service/ | 2025-06-23 | An older article (2014) discussing the early adoption of tabletop tablets by major chains to expedite service and payment.
Restaurant Technology Market Update | https://www2.hl.com/pdf/2024/hl-restaurant-technology-market-update.pdf | 2025-06-23 | A 2024 market report showing increased tech spending to combat rising costs and projecting significant growth for the global restaurant software market.
Restaurant Industry Statistics | https://www.fishbowl.com/blog/restaurant-industry-statistics | 2025-06-23 | Provides 2024 statistics showing increased tech investment by operators, digital ordering trends, and the rise of contactless payments.
US On-premise Restaurant Technology Market Report 2022 | https://store.mintel.com/us/industries/foodservice/restaurants-bars/ | 2025-06-23 | A landing page for Mintel market research reports on restaurants and bars, including a 2022 report on on-premise technology.
Tableside Ordering Systems to Improve the Dining Experience | https://www.chetu.com/blogs/technical-perspectives/tableside-ordering-systems-to-improve-the-dining-experience.php | 2025-06-23 | Discusses different types of tableside systems (QR code, mobile POS, self-service kiosks) and their benefits, such as speed, accuracy, and data collection.
Restaurant Staff Training Program | https://www.upmenu.com/blog/restaurant-training/ | 2025-06-23 | A guide on creating an effective restaurant staff training program, including menu discovery, selling tactics, and technology training.
Best Tips for Using a Restaurant Tablet Ordering System | https://themelooks.com/best-tips-for-using-a-restaurant-tablet-ordering-system/ | 2025-06-23 | Offers tips on staff training, customer education, menu optimization, and smart upselling suggestions for tablet ordering systems. Last updated May 31, 2025.
10 Advantages of Using Digital Menus in Your Restaurant | https://www.crowntv-us.com/blog/digital-menus-restaurant-advantages/ | 2025-06-23 | Lists advantages of digital menus, including increased sales, menu flexibility, cost savings, improved efficiency, and reduced wait times. Last updated August 12, 2024.
Restaurant Management Software Market Report | https://www.grandviewresearch.com/industry-analysis/restaurant-management-software-market | 2025-06-23 | Market analysis report projecting the global restaurant management software market to grow at a 17.4% CAGR from 2025 to 2030.
The Era of Digital Menus in the Restaurant Industry | https://nento.com/the-era-of-digital-menus-in-the-restaurant-industry/ | 2025-06-23 | Discusses features, pros (time/resource savings, sales improvement), and cons (staff discontent, initial expense) of digital menus.
Are Digital or Print Menus Better for My Restaurant? | https://www.onlinelabels.com/articles/are-digital-or-print-menus-better-for-my-restaurant | 2025-06-23 | Compares the pros and cons of digital versus printed menus, considering factors like durability, flexibility, cost, and customer experience.
Top 5 Digital Menu Board Trends for 2024 | https://www.eyecatch.co/top-5-digital-menu-board-trends-for-2024 | 2025-06-23 | Highlights 2024 trends like interactive touchscreens, dynamic content, personalized menus, and integration with mobile ordering.
SpotOn Named #1 Restaurant POS System in G2's Winter Report | https://www.spoton.com/blog/spoton-number-1-restaurant-pos-system-g2/ | 2025-06-23 | A press release from January 29, 2025, announcing SpotOn's #1 ranking in G2's report for restaurant POS systems.
2024 Restaurant Trends Report | https://get.popmenu.com/restaurant-resources/2024-trends-report | 2025-06-23 | Report on 2024 restaurant trends, including consumer dining decisions, operator investment priorities, and menu flexibility.
Best Restaurants Tablet for Ordering | https://www.sinsmarts.com/blog/best-restaurants-tablet-for-ordering/ | 2025-06-23 | Discusses challenges and solutions for tablet POS implementation and lists specific industrial rugged tablet models.
10 Restaurant Upselling Techniques | https://foodnhotelasia.com/blog/horeca/restaurant-upselling-techniques/ | 2025-06-23 | Provides upselling strategies like promoting complete meals, using digital menus, and offering limited-time promotions. Last updated May 22, 2025.
Benefits of Digital Menu Boards for Restaurants | https://vxt.samsung.com/blog/restaurant/benefits-digital-menu-boards-restaurants | 2025-06-23 | Outlines benefits of digital menu boards, including enhanced visual appeal, cost savings, data collection, upselling, and dynamic content management.
Digital Menu Board Trends - Updated For 2024 | https://smartersign.com/articles/digital-menu-board-trends-in-2024 | 2025-06-23 | Discusses 2024 trends, including deeper integration with POS systems, use of analytics, and lower initial investment costs.
Top Tablet POS Systems For Restaurants | https://www.merchantmaverick.com/top-tablet-pos-systems-restaurants/ | 2025-06-23 | Compares top tablet POS systems like Revel, Lightspeed, Square, Clover, Toast, and TouchBistro, providing pricing and key features.
TouchBistro Review | https://www.therestauranthq.com/technology/touchbistro-review/ | 2025-06-23 | A detailed review of TouchBistro POS, covering its pricing (from $69/month), features, and add-on costs.
The Pros and Cons of Digital Menus | https://blog.kulturekonnect.com/the-pros-and-cons-of-digital-menus | 2025-06-23 | Discusses pros (saves time, real-time updates, instant payment) and cons (waitstaff unhappiness, added expenses) of digital kiosks.
Best Point of Sales (POS) for Restaurants | https://www.wyndme.com/blog---best-point-of-sales-pos-for-restaurants | 2025-06-23 | Compares WyndMe, Toast, Square, and Shift4, with a focus on hardware and user feedback, including G2 user review summaries for Toast.
7 Must-Know Tips and Tidbits for Training Employees on Tablets | https://www.eleapsoftware.com/7-must-know-tips-and-tidbits-for-training-employees-on-tablets/ | 2025-06-23 | Provides tips for tablet-based employee training, including assessing workforce tech-savviness, creating reference materials, and ensuring data security.
Tablet Menu: 5 Reasons Why You Should Do The Switch | https://www.menutiger.com/blog/tablet-menu | 2025-06-23 | Argues for switching to tablet menus, citing benefits like maximized staff productivity, faster ordering, and increased sales through upselling. Last updated June 20, 2025.
The Pros and Cons of Using Digital Signage Menu Boards | https://www.ekaa.net/pros-and-cons-of-using-digital-signage-menu-boards.html | 2025-06-23 | Discusses pros (cost savings, enhanced customer experience) and cons (initial investment, technical issues, potential impersonal feel) of digital menu boards.
Best Restaurant POS Systems At A Glance | https://www.g2.com/categories/restaurant-pos | 2025-06-23 | G2's comparison of restaurant POS systems, listing top performers like SpotOn, Restroworks, and Square, with brief pros and cons.
How to Upsell in a Restaurant? | https://posapt.au/blogs/restaurant-upselling-techniques | 2025-06-23 | Outlines upselling techniques such as suggestive selling, highlighting specials, bundle deals, and using POS systems to track performance.
Restaurant Technology Landscape Report 2024 | https://go.restaurant.org/rs/078-ZLA-461/images/NatRestAssoc_TechLandscapeReport_2024.pdf | 2025-06-23 | National Restaurant Association report on technology use, showing customer preferences for tablets for payment and ordering, especially among younger generations.
6 Best Retail POS Systems: Ranked and Reviewed (2025) | https://learn.g2.com/best-retail-pos-systems | 2025-06-23 | G2 review of retail POS systems, with detailed user feedback on Square, Shopify, and Clover, highlighting ease of use and integration capabilities.
Tableside Ordering Restaurant Guide | https://cloudkitchens.com/blog/tableside-ordering-restaurant-guide/ | 2025-06-23 | A guide to implementing tableside ordering, covering benefits (accuracy, speed, upselling), technology selection, staff training, and customer adoption.
Worth switching from Square for Restaurants to Toast? | https://www.reddit.com/r/ToastPOS/comments/1939qwq/worth_switching_from_square_for_restaurants_to/ | 2025-06-23 | A Reddit discussion comparing user experiences with Toast and Square, covering costs, features, contracts, and customer service.
Best Point of Sale Systems For Restaurants – A Quick Look | https://koronapos.com/blog/best-pos-system-for-restaurant/ | 2025-06-23 | A comparison of various restaurant POS systems including Toast, TouchBistro, SpotOn, and Lightspeed, with pricing and key features.
The Top Restaurant Tech Trends Shaping 2025 | https://popcorngtm.com/blog/the-top-restaurant-tech-trends-shaping-2025-what-you-need-to-know | 2025-06-23 | Discusses future trends in restaurant technology, focusing on AI-powered operations, cloud kitchens, data-driven personalization, and IoT.
The Pros and Cons of Digital Menus | https://blog.kulturekonnect.com/the-pros-and-cons-of-digital-menus/ | 2025-06-23 | Inaccessible link.
Top 5 Features Your Digital Ordering System Must Have in 2025 | https://www.appfront.ai/blog/top-5-features-your-digital-ordering-system-must-have-in-2025 | 2025-06-23 | Outlines essential features for 2025 digital ordering systems, including integrated loyalty programs, data analytics, POS integration, and mobile optimization.
Best Restaurant Online Ordering Systems for 2024 | https://www.therestauranthq.com/technology/online-ordering-system/ | 2025-06-23 | Compares online ordering systems like Menufy, DoorDash Storefront, Toast, and Square, detailing fees and POS integrations.
Restaurant Technology Industry Statistics | https://www.restroworks.com/blog/restaurant-technology-industry-statistics/ | 2025-06-23 | Provides market size and growth statistics for restaurant tech, POS systems, and inventory management, along with consumer tech preferences.
TouchBistro Review | https://theretailexec.com/tools/touchbistro-review/ | 2025-06-23 | A review of TouchBistro POS, highlighting its user-friendly interface, menu management, and pricing starting at $89/month.
Your Restaurant's Order Taking Process | https://blog.zenchef.com/blog-post/your-restaurants-order-taking-process | 2025-06-23 | Discusses the benefits of using tablets for order taking, including increased efficiency, error reduction, upselling opportunities, and resource optimization.
USA Full Service Restaurants Market Forecast Report 2025-2033 | https://www.globenewswire.com/news-release/2025/06/23/3103488/0/en/USA-Full-Service-Restaurants-Market-Forecast-Report-2025-2033-Digital-Advancements-and-Healthy-Menus-Propel-Growth.html | 2025-06-23 | Market forecast report projecting significant growth for the US Full-Service Restaurant sector, driven by digital advancements.
What's The Future Of Online Ordering Systems In Restaurants? | https://orders.co/blog/future-of-online-ordering-systems/ | 2025-06-23 | Discusses future trends like centralized order management, AI-smarter menus, direct ordering websites, and integrated loyalty/marketing tools.
Lightspeed POS Reviews | https://www.lightspeedhq.com/reviews/ | 2025-06-23 | A collection of user reviews for Lightspeed POS, praising its ease of use, inventory tracking, and integrations.
Are Digital Menus Impacting Your Sales? | https://www.pushoperations.com/blog/are-digital-menus-impacting-your-sales | 2025-06-23 | Explores the benefits (customer engagement, upselling) and drawbacks (upfront costs, technical issues) of digital menus.
t'order Leads Contactless Dining Revolution | https://www.businesswire.com/news/home/20250226277321/en/torder-Leads-Contactless-Dining-Revolution | 2025-06-23 | A press release highlighting the rapid growth of tablet-based table-ordering systems, with data from provider t'order.
TouchBistro Review | https://research.com/software/reviews/touchbistro-review | 2025-06-23 | A review of TouchBistro POS, covering its features for front and back of house, security, and scalability.
The Ultimate Guide to Choosing a Restaurant Tablet Ordering System | https://www.chowbus.com/blog/restaurant-tablet-ordering-system | 2025-06-23 | A guide to selecting a POS system, with a checklist of factors to consider and a highlight of Chowbus POS features.
How to Train Staff in New Restaurant Technology | https://theprintauthority.com/how-to-train-staff-in-new-restaurant-technology/ | 2025-06-23 | Provides techniques for training staff on new technology, including using printed manuals, training managers first, and accommodating different learning styles.
How to Design an Engaging Digital Menu Board | https://www.qsrmagazine.com/growth/fast-casual/how-to-design-an-engaging-digital-menu-board/ | 2025-06-23 | Offers design tips for digital menu boards, including using quality photos, simple color palettes, and animations. Last updated Jan 27, 2025.
The POS System that Outranks the Rest | https://go.lavu.com/best-restaurant-pos | 2025-06-23 | A promotional page for Lavu POS, highlighting its #1 ranking on Capterra for functionality, ease of use, value, and customer support.
Things to consider before buying a digital menu for your restaurant | https://buonmenu.com/en/blog/things-to-consider-before-buying-a-digital-menu-for-your-restaurant | 2025-06-23 | A guide on what to consider when choosing a digital menu service, including pricing, design, photo support, ease of updates, and menu organization.
The Rise of AI-Powered Restaurant Tech | https://www.qsrmagazine.com/operations/outside-insights/the-rise-of-ai-powered-restaurant-tech-why-ordering-and-ai-innovation-isnt-just-for-the-giants/ | 2025-06-23 | Discusses the growth of AI in the restaurant industry, highlighting open, modular platforms that make AI accessible to restaurants of all sizes. Last updated Feb 6, 2025.
Lightspeed POS Reviews - Restaurant | https://www.lightspeedhq.com/reviews-restaurant/ | 2025-06-23 | A collection of user reviews for Lightspeed Restaurant POS, praising its flexibility, reporting, and customer support.
AI and the Future of Restaurant Hospitality | https://www.bottlerocketstudios.com/news-views/ai-and-the-future-of-restaurant-hospitality-2/ | 2025-06-23 | Explores how AI is enhancing restaurant hospitality through intelligent waitlist management, personalized menus, predictive inventory, and smart scheduling.
The Pros and Cons of Digital Menus | https://blog.kulturekonnect.com/the-pros-and-cons-of-digital-menus/ | 2025-06-23 | Inaccessible link.
Restaurant Tablet Best Practices: Smart Strategies For Success | https://get.chownow.com/blog/restaurant-tablet-best-practices/ | 2025-06-23 | A guide on selecting and using tablets in restaurants, emphasizing durability, system compatibility, and ease of use. Last updated Apr 11, 2025.
Restaurant Technology Market Overview | https://www.businessresearchinsights.com/market-reports/restaurant-technology-market-118085 | 2025-06-23 | A market overview projecting the restaurant technology market to grow at a 16.39% CAGR, driven by technological advancements and consumer demand.
Best Restaurant POS Systems for 2025 | https://technologyadvice.com/blog/sales/restaurant-pos-systems/ | 2025-06-23 | A comparison of top restaurant POS systems like Square, SpotOn, Toast, and Clover, with ratings on pricing, hardware, and software.
TouchBistro POS Review | https://tech.co/pos-system/touchbistro-pos-review | 2025-06-23 | A review of TouchBistro POS, covering its pricing (from $69/month), pros (strong table management), and cons (iPad only, no free trial).
Restaurant Tablet Best Practices | https://solink.com/resources/industry-insights/restaurant-tablet-best-practices/ | 2025-06-23 | Provides best practices for using tablets, including investing in durable models, thorough staff training, and integration with POS systems.
What is the Best Restaurant POS System? | https://tech.co/pos-system/best-restaurant-pos-systems | 2025-06-23 | Ranks and reviews restaurant POS systems, naming Toast as the best overall for its user experience and features.
Best Restaurant POS Systems | https://www.restroworks.com/blog/best-restaurant-pos-systems/ | 2025-06-23 | A listicle comparing 14 POS systems, including Restroworks, Square, and Toast, with key highlights, pros, cons, and Capterra ratings.
5 Best Restaurant Online Ordering Systems | https://www.tryotter.com/blog/toolkit/5-best-restaurant-online-ordering-systems | 2025-06-23 | Reviews comprehensive restaurant management systems for 2025, including Otter, PopMenu, and ChowNow, highlighting their unique features.
How to design a digital menu | https://www.lightspeedhq.com/blog/digital-menus-for-restaurants/ | 2025-06-23 | Provides best practices for digital menu design, including font/color choice, menu engineering, writing descriptions, and incorporating visuals.
Lightspeed Restaurant POS Review 2025: Features and Pricing | https://www.nerdwallet.com/reviews/small-business/lightspeed-restaurant-pos | 2025-06-23 | A review of Lightspeed Restaurant POS, detailing its features, pricing, pros (advanced inventory, CRM), and cons (extra cost for accounting sync).
A 10 Step Guide to Restaurant POS System Training with Your Staff | https://www.touchbistro.com/blog/a-10-step-guide-getting-your-staff-onboard-with-your-new-restaurant-pos/ | 2025-06-23 | A guide for training staff on a new POS system, with steps like involving staff early, conducting dry runs, and nurturing "superstars".
Lightspeed Restaurant POS Review | https://www.therestauranthq.com/technology/lightspeed-restaurant-pos-review/ | 2025-06-23 | A review of Lightspeed Restaurant POS, covering its pricing, features, and user reviews, noting its strong reporting and inventory tools.
Restaurant Trends 2024: What's Shaping the Industry | https://salesplay.com/restaurant_industry-trends/ | 2025-06-23 | Discusses 2024 restaurant trends, including the digital transformation through online ordering, contactless payments, and data analytics.
Digital Menu Best Practices | https://wanddigital.com/digital-menu-best-practices/ | 2025-06-23 | Offers best practices for digital menu design, covering layout, colors, fonts, photography, dayparting, and A/B testing.
Best Paid & Free Alternatives to Restaurant Point Of Sale | https://www.g2.com/products/restaurant-point-of-sale/competitors/alternatives | 2025-06-23 | G2's list of alternatives to generic "Restaurant Point Of Sale" software, with user ratings for Square, Toast, SpotOn, etc.
Toast vs. Square: A Full Comparison for All Business Types | https://www.owner.com/blog/toast-vs-square | 2025-06-23 | A detailed comparison of Toast and Square, covering features, pricing, hardware, and customer service.
Managing Turnover with Effective iPad POS Training | https://madmobile.com/blog/managing-turnover-with-effective-ipad-pos-training/ | 2025-06-23 | Provides best practices for training staff on an iPad POS system, including assessing tech comfort and using interactive learning methods.
5 restaurant tech trends to enhance hospitality in 2024 | https://www.exploretock.com/join/resources/restaurant-technology-trends-2024/ | 2025-06-23 | Discusses 2024 tech trends like voice ordering, reservation platforms, and integrated POS systems to enhance personalization and profit.
Automated Ordering Systems for Restaurants | https://limetray.com/blog/automated-ordering-systems-restaurants/ | 2025-06-23 | Explains the benefits of automated ordering systems and provides a step-by-step guide for implementation.
Lightspeed Pro Review | https://www.business.com/reviews/lightspeed-pro/ | 2025-06-23 | A review of Lightspeed POS, rating it highly for its features, ease of use, and customer service, particularly for retail businesses.
Modernizing Eateries: Integrating Digital Ordering Systems | https://thebossmagazine.com/modernizing-eateries-integrating-digital-ordering-systems/ | 2025-06-23 | Discusses the benefits of digital ordering systems and emerging trends like AI-driven personalization and voice-activated ordering.
Why choose Toast vs Square/Clover/other POS? | https://www.reddit.com/r/ToastPOS/comments/1ijio2a/why_choose_toast_vs_squarecloverother_pos/ | 2025-06-23 | A Reddit discussion comparing user experiences with Toast, Clover, and Lightspeed, highlighting Toast's user-friendliness and integrations.
Toast vs. Square: Which POS System Is Best for Your Business? | https://technologyadvice.com/blog/sales/toast-vs-square/ | 2025-06-23 | A detailed comparison concluding Toast is better for mid-to-large restaurants and Square is better for small food businesses.
The Future of Restaurant AI: How Smart Technology is Reshaping the Industry | https://www.katalystos.com/blog/the-future-of-restaurant-ai-how-smart-technology-is-reshaping-the-industry | 2025-06-23 | Explores the role of AI in restaurants in 2025, covering predictive analytics, intelligent automation, personalized loyalty programs, and dynamic pricing.
9 Digital Menu Board Design Tips for Restaurants | https://vxt.samsung.com/blog/restaurant/restaurants-digital-menu-board-design-tips | 2025-06-23 | Provides design tips for digital menu boards, including hierarchy, legibility, branding, imagery, simplicity, motion, and accessibility.
Best POS Software | https://www.g2.com/categories/pos | 2025-06-23 | G2's landing page for POS software, listing top-rated systems for retail.
TouchBistro vs. Clover: Which POS Is Better for Your Business? | https://staxpayments.com/blog/touchbistro-vs-clover/ | 2025-06-23 | Compares TouchBistro (iOS-based) and Clover (Android-based), detailing TouchBistro's pricing structure with its various add-ons.
6 Things to Consider When Designing a Digital Menu | https://blog.rockbot.com/best-practices-digital-menu | 2025-06-23 | Design considerations for digital menus, focusing on clarity, content management, and brand customization.
The Future of Online Food Ordering: AI, Drones, and Beyond | https://foodtech.folio3.com/blog/ai-ordering-system-in-food-delivery/ | 2025-06-23 | Discusses the role of AI in online food ordering, including personalized recommendations, conversational ordering, and route optimization for delivery.
Toast vs. Square: A Full Comparison for All Business Types | https://www.gravityforms.com/blog/toast-vs-square-full-comparison-for-all-business-types/ | 2025-06-23 | Compares Toast (restaurant-focused) and Square (full-service payment processor), detailing their functionality, hardware, and payment processing models.
Upselling Techniques in Restaurants: A Guide to Boosting Your Sales | https://www.chowbus.com/blog/upselling-techniques-in-restaurants | 2025-06-23 | Focuses on preparing staff for effective upselling through training, role-playing, and incentives.
The future of restaurants: How AI and other tech can help elevate the experience | https://www.deloitte.com/us/en/Industries/consumer/articles/future-of-restaurants-and-ai.html | 2025-06-23 | A Deloitte survey showing restaurant leaders are leveraging technology, including AI, to improve order accuracy and streamline workflows.
What's The Future Of Online Ordering Systems In Restaurants? | https://orders.co/blog/future-of-online-ordering-systems/#:~:text=The%20next%20evolution%20includes%20deeper,working%20together%20in%20one%20platform. | 2025-06-23 | Discusses the future evolution of online ordering systems, including deeper integration of marketing, fulfillment, and customer engagement tools.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | Average ticket time: apps=8min; entrees=12-15min | How can we improve ticket times? | Ticket times | FALSE
Customer satisfaction | Check-out time: >1min | Are customers satisfied with checkout processes? | Customer satisfication | FALSE
Customer satisfaction | Technical issues: >5% reported | How can we improve customers' ability to use the tablets? | Technical issue reports | TRUE
Customer satisfaction | Order accuracy: 100% | Should we continue using the tablets? | Order accuracy for tablets vs servers | TRUE
Customer satisfaction | Wait time: >10min | How can we improve wait times for customers? | Reported wait times | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer satisfaction | This question gathers data on menu item popularity. It helps in understanding customer preferences and can inform inventory management, menu engineering, and promotional strategies. | - Order Frequency: Count/percentage for each menu item selected. &lt;br> - Item Combination Analysis: Identifies which items are frequently ordered together. | During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Customer satisfaction | This question assesses the adoption and utility of the tablet for re-ordering. It indicates whether customers find the tablet convenient for continuous use throughout their meal. | - Re-order Rate: Percentage of customers who used the tablet for multiple orders (Yes/No). | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
Customer satisfaction | This is a standard customer satisfaction question focused specifically on the tablet technology. It provides a quantifiable measure of the overall user sentiment towards the tablet. | - Average Satisfaction Score: Mean score (e.g., 4.2 out of 5). &lt;br> - Net Promoter Score (NPS) or Top-Box/Bottom-Box Score: Percentage of promoters (5s) vs. detractors (1-3s). | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 - Lacking | 2 | 3 | 4 | 5 - Great
Customer satisfaction | This question evaluates the effectiveness of the staff in introducing and explaining the new technology to customers. It helps determine if staff training is adequate. | - Instruction Quality Rating: Can be a scale (e.g., Very Well, Adequately, Poorly) or a numerical average if a scale is used. | How well did your waiter instruct you how to use the tablet? | Scaled | 1 - Not well | 2 | 3 - Very well
Customer satisfaction | This question measures the user-friendliness and intuitiveness of the tablet's interface. It directly assesses the User Interface (UI) and User Experience (UX) design. | - Customer Effort Score (CES): Average rating indicating the ease of use. Lower scores might point to specific navigational issues needing improvement. | On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 - Difficult | 2 | 3 | 4 | 5 - Easy
Customer satisfaction | This question measures a key aspect of front-of-house efficiency. The data can be used to identify bottlenecks in seating and improve wait time management. | - Average Wait Time: Mean or median time reported by customers (e.g., in minutes). | On average, how long did you wait for your table? | Scaled | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Customer satisfaction | This question helps to understand the total dining duration. It can be cross-referenced with tablet usage to see if the technology impacts the length of a meal (either shortening or extending it). | - Average Dining Duration: Mean or median time spent at the restaurant. | On average, how long did your dinner take? | Scaled | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min.
Customer satisfaction | This question is a direct measure of kitchen accuracy. It's a critical key performance indicator for back-of-house operations. | - Order Accuracy Rate: Percentage of "Yes" responses. | Did the kitchen prepare your order correctly? | Yes/No | Yes | No | If no, what went wrong?
Customer satisfaction | This question assesses customer sentiment regarding the payment process on the tablet. It uses a statement to gauge agreement on the specific attributes of speed, ease, and security. | - Agreement Level: Can be measured using a Likert scale (e.g., Strongly Agree to Strongly Disagree). The percentage of positive responses (Agree/Strongly Agree) is a key indicator. | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/false | TRUE | FALSE | If you don't agree with the above statement, why?
Customer satisfaction | This question specifically measures customer trust and perceived security in the tablet payment system. It's crucial for understanding barriers to adoption for a key function. | - Confidence Level: Average score on a rating scale (e.g., Very Confident to Not Confident at All) or a numerical scale (1-5). | How confident are you in submitting your payment through a tablet? | Scaled | 1 - Not at all | 2 | 3 | 4 | 5 - Very confident
Customer satisfaction | This measures the effectiveness of the tablet as a marketing and customer acquisition tool. It evaluates a specific call-to-action within the tablet interface. | - Conversion Rate: Percentage of customers who signed up (Yes/No). | Did you sign up for the newsletter on the tablet? | Yes/No | Yes | No
Customer satisfaction | This is a comparative question that directly evaluates the perceived value of the new tablet system against the traditional service model. It helps to understand if the technology is seen as an improvement. | - Comparative Preference Score: Can be a scale (e.g., Much Better, Better, About the Same, Worse, Much Worse). The percentage of customers who rate the tablet experience as "Better" or "Much Better" is a primary indicator. | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | I liked the tablet experience better, and would like that going forward. | I would like a mix of tablet ordering at the table and waiter interaction. | I disliked the tablets, and would rather have a waiter. | I found both experiences comparable and it doesn't matter either way.
Customer satisfaction | This question is a direct inquiry into the reliability and performance of the hardware and software. It helps identify the frequency of technical problems, which is crucial for troubleshooting, maintenance, and assessing the overall stability of the tablet system. A "Yes" answer would typically lead to a follow-up question asking for details about the issue. | - Technical Issue Rate: The percentage of users who reported experiencing a technical issue (Yes/No).&lt;br>- Issue Categorization (from follow-up): If details are collected, indicators could include the frequency of specific problems (e.g., "tablet froze," "payment failed," "couldn't connect to Wi-Fi"). | Did you have any technical issues with your tablet? | Open-ended